# Text boxes

| Issue Ref. | Action | Lead Partners | Current Situation | Timescale |
| --- | --- | --- | --- | --- |
| Leisure, Tourism and Heritage |
| LTH 1 | To develop a sustainable tourism plan which looks beyond the current funding arrangement with Anglian Water. Rutland Tourism Strategy already exists and plans have been incorporated into the tourism team work programme to refresh this strategy. | Rutland County Council (Emma Savage) Anglian Water (AW) | A 5 year agreement for funding Discover Rutland began in 2007 | By April 2011 |
| LTH 2 | To build links between Rutland Water activities and events taking place in Oakham, Uppingham and surrounding areas. | RCC (Emma Savage) Arts 4 Rutland OTC /OTP/UTC Oakham Festival | Included in programme of Discover Rutland | By April 2010 |
| LTH 3 | To review the impact on tourism and the economy that the Annual Bird Fair has and how these can be developed further. | RCC (Emma Savage) L+RWT OTC AW | Included in programme of Discover Rutland | By May 2010 |
| LTH 4 | To extend walking, cycling and horse riding routes around the Rutland Water area, by making connections with existing routes and/or reclassifying existing routes. | RCC (Highways), Anglian Water CPRE Bridleways Association | Several possible routes being explored for improvement | April 2011 |
| Highways, Transport and Access |
| HTA 1 | To review parking provision around Rutland Water and make recommendations on improvements required (if any) | RCC (Highways) Parish Councils Anglian Water L+RWT Natural England | No recent review except in Hambleton | September 2010 |
| HTA 2 | Improve public transport links between Rutland Water and Oakham and Uppingham | RCC (Highways) Parish Councils Anglian Water | Limited bus provision on weekday. None at all on Sundays | June 2010 |
| HTA 3 | Complete a safe off-road circuit around Rutland Water for cyclists | RCC (Highways) Anglian Water Parish Councils Natural England | Some small sections e.g. Lyndon, are still on public roads | September 2011 |
| HTA 4 | To work towards a Higher Level Stewardship (HLS) agreement to extend and improve public access to areas around the reservoir. N.B. Government has removed funding attached to HLS access, therefore this is no longer a priority. | Anglian Water English Nature RCC (Highways) Parish Councils Ramblers Association Bridleways Association | To establish an agreement by April 2011 | By April 2012 |
| Environmental Quality |
| EQ 1 | To review the boundary of the Rutland Water special policies area. The boundaries to Rutland Water Policy Area and defined Recreation Areas will be reviewed through the LDF Site Allocations and Development Control Policies Document. | RCC (David Troy) Anglian Water NFU Parish Council Natural England | Boundary for special policies is that contained with LDF Core Strategy | September 2011 |
| EQ 2 | To develop and promote environmentally sensitive farming in the Rutland Water catchment area in order to contribute to the reduction of phosphate levels with Rutland Water SSSI, which may contribute to the formation of blue/green algal blooms. | NFU Anglian Water Natural England Environment Agency L+RWT | Situation update required Promotional plan required | March 2010 October 2010 |
| EQ 3 | To develop and promote the Landscape Strategy (part of the RCC Biodiversity Action Plan) in respect of the Rutland Water Area | RCC (Craig Howat) L+RWT NFU Natural England Anglian Water | Landscape Strategy drafted for discussion | May 2010 |
| EQ 4 | Where possible, to contribute to the improvement of biodiversity within the Rutland Water area and to receive annual reports on progress on managed sites within the Rutland Biodiversity Action Plan. | Natural England L+RWT Anglian Water NFU Users Group RCC | No summary report available yet | December 2010 |
| EQ 5 | To receive information on and comment on actions to reduce greenhouse gas emissions, including carbon dioxide, by the adoption of energy saving practices and other relevant measures within the area. (N.B. this is included so that members are fully aware of initiatives within the area.) | RCC (Isabel Clark) Anglian Water NFU L+RWT Parish Councils Users Group | The programme is stated within the Carbon Management Plan | September 2010 |
| EQ 6 | To receive and comment upon information relating to the assessment of potential risks and opportunities to the Rutland Water area resulting from climate change and where possible, implement measures to reduce priority risks and pursue opportunities. | Anglian Water RCC (Isabel Clark) NFU L+RWT Parish Councils Users Group | The programme is stated in the Climate Change Action Plan | October 2010 |